Proposal Artifact · Staffing & Teaming

Staffing & Teaming Plan

Personnel structure, work-share, and dual-lane teaming construct

Prepared for:  U.S. Department of Veterans Affairs — Veterans Health Administration

Solicitation:  36C77626Q0191  (NAICS 541990)

Author:  Jelani House, Engagement Manager

Firm:  House Strategies Group, LLC  ·  SBA 8(a) / SDB

Date:  May 31, 2026

Contact:  jelani@housestrategiesgroup.com  ·  (434) 981-5295

Prepared for U.S. Department of Veterans Affairs — Veterans Health Administration in response to Sources Sought 36C77626Q0191. Real figures are sourced from BLS OEWS (2025) and VA OIG (FY2025); commercial-survey blends and VHA-current pay are illustrative pending licensed surveys and the VHA HR extract. Independent submission — not affiliated with or endorsed by the U.S. Department of Veterans Affairs.

1.  Teaming structure — dual-lane

The team fields a compliant prime in either acquisition lane. The compensation methodology and Task 4 platform are HSG-built and stay with HSG in both.

Lane A — SDVOSB Joint Venture (if VA invokes Vets First, 38 U.S.C. §8127):

| Firm | Role | Work-share |
| --- | --- | --- |
| Riley McGuire Partners (SDVOSB) | Managing venturer — survey operations + program management | 45% |
| House Strategies Group (8a/SDB) | JV partner — compensation-analysis engine + Task 4 platform | 40% |
| Emax (WOSB) | Analytical surge subcontractor | 15% |

Lane B — HSG 8(a) prime (if 8(a) or open):

| Firm | Role | Work-share |
| --- | --- | --- |
| House Strategies Group (8a/SDB) | Prime — single point of accountability; self-performs analytical core | 68% |
| Riley McGuire Partners (SDVOSB) | Service-Disabled Veteran subcontractor — survey operations | 17% |
| Emax (WOSB) | Analytical surge subcontractor | 15% |

Critical dependency: RMP must hold an active SBA-certified SDVOSB status and self-perform ≥40% of the JV's work (survey operations + PM) for Lane A to be compliant.

2.  Personnel structure — HSG core team

| Key personnel | Title | Study role | PWS | Alloc. |
| --- | --- | --- | --- | --- |
| Jelani House | Founder & Managing Director | Engagement Manager / Project Director & Task 4 Platform Owner | All tasks · Task 4 lead | 12% |
| Raina Cook | Senior Compensation Analyst | Market Benchmarking Lead | Task 2 (lead) · Task 1 | 20% |
| Gilda Weech-House | Senior HR Officer (Ret.), CJE | Job-Architecture Lead | Task 5 (lead) · Task 2 | 16% |
| Michael Nelson | Senior Consultant | Data Operations & Crosswalk Lead | Task 4 (4C–4D) · Task 2 | 14% |
| Joel V. Sutherland, MA | Classification & Compliance Analyst | Title 5 / FLSA & SSR Specialist | Task 5 · SSR packages | 10% |
| Laverne A. Cunningham | Senior HR SME | Survey Licensing & Physician-Pay Panels | Task 1 (lead) · Task 2 | 14% |
| Amy Han | Analyst | Geographic Differentials, QA & Production | Task 3 · all deliverables QA | 8% |

3.  Capability assessment

•  Strengths: federal classification (State Dept / OPM FES), Title 5 + SSR, survey licensing, data-ops & crosswalk, and the HSG-owned Task 4 platform.

•  Priority add: a Healthcare Provider-Compensation SME with §7431 physician-pay-panel and SullivanCotter/MGMA/AMGA depth — the one gap relative to the clinical core of the work.

•  Secondary: confirm RMP fields a §7451 Survey-Operations lead; add a cloud/data engineer behind Data Ops for Task 4 production.

Approval

| Prepared — Jelani House, Engagement Manager | Reviewed — HSG Compensation Lead | Approved — VA Compensation Authority |
| --- | --- | --- |